## Hoja1
Product Backlog |  |  |  | Sprints
Item Id | Description | Responsible | Effort | Id | Start Date | End Date | Goal
I1 | AS a User I WANT TO Log in SO THAT the system provides the functionalities enabled for my role | Javier Jaen | 270 | 1 | 2025-09-10 | 2025-09-24 | Support features to authenticate users
I2 | AS a User I WANT TO Log out SO THAT my work session ends | Javier Jaen | 50 | 2 | 2025-09-25 | 2025-10-09 | Support features for Service Head
|  |  |  | 3 | 2025-10-10 | 2025-10-24 | Support features for Area Masters
|  |  |  | 4 | 2025-10-27 | 2025-11-10 | Suppot features for Operators
320
Sprint 01 Backlog
Task Id | Description | Responsible | Effort
T1.1 | Code the credentials business layer | Bad Bunny | 40
T1.2 | Code the user business layer | Harry Potter | 40
T1.3 | Code the persistence layer | David Broncano | 40
T1.3 | Code the UI | Maria López | 80
T1.4 | Test the Credentials and user persistence | Harry Potter | 40
T1.5 | Test the business layer | David Broncano | 40
T1.6 | Test the UI | Bad Bunny | 40
320